Catering Manager’s Role

Providing food for 200 people for 24 hours or food for 400 people for 6 hours initially sounds a scary thing but the VRA has a detailed manual (available from the Volunteer Recruitment Officer) and several experienced rogaine caterers who can advise you how to manage the food production to be a successful experience. You do not have to be a gourmet cook, but you do need a few hours to organise the menu, the purchase of the food and its transport to the event.  You will also need to direct the team of very willing helpers on the event day.

# What you will do in the weeks before

- Read the catering manual, locate some helpers (the Volunteer Recruitment Officer will help you) find out about the hash house location from the event coordinator.

- If you have the opportunity at the event before you cater checkout the equipment available or find out from the Equipment Officer what equipment and leftover food is available from the store

- Contact the Event Treasurer who will give you a budget and a money advance, which you will pay into your bank to pay for the food.

- Decide what you want people to eat. Work out your menu in quantities for a hundred people and multiply when final numbers are known. You can be very creative in your food selection or follow one of the many previous menus and use the recipes, which are in the catering manual. You will also need to plan the purchase of cleaning materials, toilet paper and special food for the helpers.

- Locate where you are going to purchase the food and method of payment.

- Contact and arrange for some of your helpers to purchase and transport the food to the event.

When you know final numbers of competitors (approx. one weekend before) Find our from Admin        Manager

- Finalise your quantities   Prepare and print recipes and preparation instructions

- Order perishable food such as meat, bread, vegies and fruit to be either picked up or delivered to the person who is to transport it on the day. Buy groceries and cleaners. Make sure you collect receipts for all money you or your helpers spend.

- Finalise with your helpers food buying and transport to the event.- eskys, ice and cars

On the day of the event

- Transport food to event. The equipment transport team will probably have set up the marquee before you arrive.

- Organise set up and cleaning of the equipment. Think about how the food is to be prepared and served.

- Provide lunch for helpers, introduce them to each other and instruct them in food safety (information in manual), In longer events organise a roster of your helpers roles and times of work.

- Give out recipes and organise helpers into the preparation of the food (detailed timelines in the manual)

- Ensure that the food is safely stored and the working area is kept clean.

- You direct your helpers and do very little food preparation yourself.

- Serve food. In longer events food will need to be prepared in smaller batches and served over a long period.

# After everyone has eaten

- Organise the final clean up and pack up of equipment, make up a list of the non perishable food, give away perishable food, organise the disposal of rubbish.

- Collect all receipts from helpers, finalise  payment to any helpers or give them expense claim forms

# After the event

- Finalise accounts with Event Treasurer.

Don’t be put off being Catering Manager. It is a bit of work but is also fun and rewarding. The competitors will be very appreciative of your efforts when they come in tired and hungry to eat your feast. Remember you do not have to do every thing yourself. Rogainers are very willing, capable helpers and there are lots of experienced people who can give you advise. Make up a team of your  friends to help you or share the role